## Tabelle1
Roadmap

	Alpha	Beta	Gamma	Delta	Epsilon
Design/Art	- three basic maps drawn / (finish NPC houses) / - assets for basic maps drawn / - Base Sprite for all NPCs / - Basic SpriteSheet for Protag	- complete basic sprite sheets / for all NPCs / - different crops for farming / - improved SpriteSheet for / Protag / - interior design of all houses / - first interior design of tower / - close up faces for dialogue
Gameplay	- walk around with working / camera / - switch between maps / - working entrance to tower / - be able to interact with NPCs	- NPCs have basic behaviour / - basic attack action / - first basic monster encounter / - different levels for tower that / Are accessable
UI/UX	- basic skill tree / - basic bar for items/health/etc / - basic inventory	- switch between items in bar / - include skill points that you / can spend / - xp bar / - display for stats
Story	- basic backstory for all NPCs / (one paragraph for each) / - write down short version of / Story (one paragraph) / - write backstory for protag / (one paragraph)	- expand on course of the / Story
Sound/Music	-x-	- include sound effects / (walking, attacking, text / Scrolling, etc…)
Optimization	-x-	- optimize animations